## Sprint1
Sprint 1 :
OBJECTIVES : | 1. DataBase Design | 2. DataBase Creation and Connection | 3.Home page | 4.Module for Buying an Insurance
DURATION :
User Story | TO DO | In Progress | Impediment | To Verify | Done | Assigned To
Database design | creating the database design according to the project requirment . |  |  |  | done | AAKASH SUNILBHAI PATEL
1. Customer Login, Admin Login, Admin Approval[Riya Hoondlani] | [5 empty] | Sharanabasappa
1. Customer Login, Admin Login, Admin Approval[Riya Hoondlani] | [5 empty] | Mangala vamsi krishna
1. Customer Login, Admin Login, Admin Approval[Riya Hoondlani] | [5 empty] | SaiSindhu Nomula
Database Creation and connection | Create the database and connect it to the backend using EF-DB first method |  |  |  |  | SaiSindhu Nomula
Home Page | 1.Develop a home page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for home page (backend) 3 . Integrate the frontend backend |  |  |  | done | Mangala vamsi krishna
Registration Page[buy insurance] | 1.Develop a Registration page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Registration page (backend) 3 . Integrate the frontend backend |  |  |  | done | SaiSindhu Nomula
Fetching Vehicle details [Buy Insurance as title of page ] | 1.Develop a Buy insurence page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Buy Insurence page (backend) 3 . Integrate the frontend backend |  |  |  |  | Sharanabasappa
Fetching Policy plan details [Plans as the title of the page ] | 1.Develop a Plan page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Plans page (backend) 3 . Integrate the frontend backend |  |  |  | done | AAKASH SUNILBHAI PATEL
Validating all webpages | Developing some custom validators and using some default validators and validating the forms to take the appropriate input from the user |  |  |  | done | AAKASH SUNILBHAI PATEL

## Sprint2
Sprint 2 :
OBJECTIVES : | Claim insurance Module | Renew Insurance Module | Admin Module
DURATION :
User Story | TO DO | In Progress | Impediment | To Verify | Done | Assigned To
Design for Renew insurance page and admin page | Design for Claim insurance page |  |  |  | done | SaiSindhu Nomula
Renew Insurence Page | 1.Develop a Claimpage component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Renew page (backend) 3 . Integrate the frontend backend | backend |  |  | front end and backend done | Sharanabasappa
Claim Insurance | 1.Develop a Claim page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Claim page (backend) 3 . Integrate the frontend backend |  |  |  | done | AAKASH PATEL
1. Admin page | 1.Develop a Claim page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Claim page (backend) 3 . Integrate the frontend backend |  |  |  |  | Mangala vamsi krishna

## Sprint 3
Sprint 3 :
OBJECTIVES : | 1. Calculate Premium Module | 2. Login Page
DURATION :
User Story | TO DO | In Progress | Impediment | To Verify | Done | Assigned To
LOGIN page | 1.Develop a Login page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Login page (backend) 3 . Integrate the frontend backend |  |  |  | front end done | AAKASH SUNILBHAI PATEL
Calculate premium ----- 4 Wheeler | 1.Develop a Calculate premium page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Calculate page (backend) 3 . Integrate the frontend backend |  |  |  | done | SaiSindhu Nomula
Calculate premium ----- 2 Wheeler | 1.Develop a Calculate premium page component in the angualar (frontend) 2. Develop the services, repositories, Controllers , Interfaces etc which are required for Calculate page (backend) 3 . Integrate the frontend backend |  |  |  | done | Sharanabasappa
Foget password | 1.Develop the services, repositories, Controllers , Interfaces etc which are required for Forget Password (backend) 2.. Integrate the frontend backend |  |  |  |  | MangalaVamsi
Reset password | 1.Develop the services, repositories, Controllers , Interfaces etc which are required for reset password (backend) 2.. Integrate the frontend backend |  |  |  |  | SaiSindhu Nomula